University Statement:

**Implementation Timeline – Update (15 October 2024)**

|  |  |  |  |
| --- | --- | --- | --- |
| **Actions** | **Who** | **When** | **Progress** |
| * Briefing on Assemblies
 | Tavis Potts/Fraser Lovie | 1pm 17/6/24 | ***Complete*** |
| * Agreement on first ESG topic for the Assembly, size, date etc.
 | Tracey Slaven | Wk of 1/7/24 | ***Agreed*** “How can the University respond to international conflict” |
| * Announcement of Assembly
 | Tracey Slaven | Wk of 8/7/2024 | ***Complete:***4 July 2024 |
| Implementation phase will see design of session, representative audience design etc, invites issued early Autumn. |  |
| * 1st Assembly
 |  | Late 2024/early 2025 | ***Underway:***Arrangements for event underway |
| * Report/implementation plan
 |  | February 2025 |  |

**Citizen Assembly**

|  |  |  |  |
| --- | --- | --- | --- |
| **Action** | **Who** | **When** |  |
| * Update to Senate
 | Tracey Slaven | 5 June  | ***Complete*** |
| * Ongoing dialogue with British Council – awaiting proposal on HESPAL
 | Ashar Eshan Approval by SMT | For academic year 2024/25 | Proposal being developed with a view to implementing scholarship from Session 2025/26 (in line with BC timescales) |
| * Inclusion of scholarships in new fundraising campaign
 | Court | June 2024 Court | ***Complete*** |

**Support for Palestinian academics, students, and knowledge workers.**

**Sustainable Investment Policy**

|  |  |  |  |
| --- | --- | --- | --- |
| **Action** | **Who** | **When** |  |
| * Engagement with APUC
 | Tracey Slaven | End of July | Laptop supply framework - HP split into 2 completely separate companies some years ago - HP Inc. and Hewlett Packard Enterprise (HPE). HPE is listed in relation to occupied territories in Palestine, whereas HP laptops come from HP Inc. HP Inc. has advised that both companies operate independently of each other with no degree of joint ownership or control. |
| * Review potential/practicality of extending exclusions to the wider arms sector.
 | Tracey Slaven   | Investment Committee * 19 June
* 26 September
 | Analysis identifies that Pooled funds prevent extension of Policy at this time. As new pooled funds emerge this can be reviewed.Commitment to transparently report level of investment in the sector on a regular basis. |
| * Review potential/ practicality of extending exclusions to include the UN listing of companies in the OPT.
 | (as above) | (as above) | Pooled fund management means exclusion is not possible |