University Statement:

**Implementation Timeline – Update (4 July 2024)**

|  |  |  |  |
| --- | --- | --- | --- |
| **Actions** | **Who** | **When** | **Progress** |
| * Briefing on Assemblies
 | Tavis Potts/Fraser Lovie | 1pm 17/6/24 | ***Complete*** |
| * Agreement on first ESG topic for the Assembly, size, date etc.
 | Tracey Slaven | Wk of 1/7/24 | ***Agreed*** “How can the University respond to international conflict” |
| * Announcement of Assembly
 | Tracey Slaven | Wk of 8/7/2024 | ***Complete:***4 July 2024 |
| Implementation phase will see design of session, representative audience design etc, invites issued early Autumn. |  |
| * 1st Assembly
 |  | Pre-December diet | ***Date set:***4 December 2024 |
| * Report/implementation plan
 |  | February 2025 |  |

**Citizen Assembly**

|  |  |  |  |
| --- | --- | --- | --- |
| **Action** | **Who** | **When** |  |
| * Update to Senate
 | Tracey Slaven | 5 June  | ***Complete*** |
| * Ongoing dialogue with British Council – awaiting proposal on HESPAL
 | Ashar Eshan Approval by SMT | For academic year 2024/25 |  |
| * Inclusion of scholarships in new fundraising campaign
 | Court | June 2024 Court | ***Complete*** |

**Support for Palestinian academics, students, and knowledge workers.**

|  |  |  |  |
| --- | --- | --- | --- |
| **Action** | **Who** | **When** |  |
| * Engagement with APUC
 | Tracey Slaven | End of July |  |
| * Review potential/practicality of extending exclusions to the wider arms sector.
 | Tracey Slaven   | Investment Committee * 19 June
* 26 September
* 19 December
 | Review requested |
| * Review potential/ practicality of extending exclusions to include the UN listing of companies in the OPT.
 | (as above) | (as above) |  |

**Sustainable Investment Policy**